## Bugs & Fixes
Bugs & Fixes — session log
Build | Issue | Root cause | Fix | Status
2026.06.18.~ | Deploys not reaching devices ('nothing changed') | Service-worker CACHE_NAME wasn't bumped (a manual, easily-missed deploy step), so installed PWAs kept the cached bundle. | build now derives CACHE_NAME from a content hash of app.js+data.js+index.html — auto-invalidates every deploy. | Fixed
2026.06.18.3 | Horizontal scroll in Library → word Browse on narrow phones; the 'Known' button overhung the card edge | CSS grid blow-out: grid tracks are auto-sized and items default to min-width:auto, so cards couldn't shrink below their content. | Grid -> minmax(0,1fr); card minWidth:0; left column flex:1 + every text line ellipsised. Verified 280-390px. | Fixed
2026.06.18.6 | Bottom tab bar raised up; dead gap (~1/8 screen) below it | The global overflow-x:hidden guard added in the fix above forced overflow-y:auto, turning the BODY into a scroll container; on mobile a fixed bottom bar then references the smaller layout viewport. | Removed the html/body overflow guard (overflow already prevented at source by the grid fixes). Body overflow-y back to 'visible'. Left a warning comment. | Fixed

## Next-Up (post-audit)
Next-Up — reprioritised after the deep audit (my recommendation)
Order reflects what I learned actually building & auditing the app: friction-cuts and data-integrity rise; canvas/Browse polish falls (worst parts already done, and typed-mode 'void' is keyboard space); speaking stays the big learning bet; tutor last (per direction).
# | Initiative | Why now (post-audit rationale) | Effort | Risk
✓ | Configurator -> presets + Advanced [DONE v2026.06.18.7] | Biggest friction-per-effort: the 5-axis setup modal gates EVERY session start and is shared by Home/Library/Train launches, so one change has broad reach. Pure layout. | Low-Med | Low
2 | Validate CEFR tags -> truthful B2 % | Audit found only ~1,000 of 2,001 words have a real CEFR level; the rest are guessed from difficulty (only 3 are tagged A1). The whole 'journey to B2 %' rests on this. Data task. | Med (data) | Low
3 | PWA reminders / re-engagement | The one retention lever still untouched. SRS apps live or die on the return trigger; 'you have N reviews due' as a notification is exactly the honest hook this app should own. | Med | Low-Med
✓ | Aspirational empty states [DONE v2026.06.18.8] | Quick first-week 'aha': a brand-new user's Stats is a wall of zeros. Low effort, contained. | Low | Low
5 | Personalised weak-spot deck | Data already exists (per-card miss counts + the Weak queue). Turn it into a first-class 'drill your weak spots' deck. Real learning value, modest build. | Med | Low
6 | Speaking production mode | The biggest remaining LEARNING gap — B2 means speaking, and the app trains none. Web-Speech de-DE shadowing + scoring; speechSynthesis (output) already wired, recognition (input) is the new part. | High | Med
7 | Finish session-canvas composition (MC/tap screens) | DOWNGRADED. Worst offenders (answered state, recall card) already composed, and typed-mode 'void' is keyboard territory. Remaining: port the Audio bottom-anchor to the article/verb-MC/sentence screens. | Med | Low
8 | Curated Browse (grouping / sticky letters) | DOWNGRADED. Overflow fixed and search works, so the flat list is usable; curation is now polish, not a pain point. | Med | Low
9 | Relocation scenario packs + reposition | Identity bet (the defensible niche). Content + copy heavy; sequence after the friction/retention wins land. | Med-High | Med
10 | AI-graded writing | Pairs with the tutor; needs the hosted proxy. Real B2 'write to the Bürgeramt' value. | High | Med
11 | AI Tutor productisation | Deferred per your direction — the premium-tier capstone, do last. Needs metered hosted proxy. | High | Med
Already shipped this session (for context):
Layered 'Strong' progress · Due-as-hero · one-verdict answered state · vocab-in-context · listening-first · faster chapters · grammar (modal/separable) fix · tap-driven icon animations + cog redesign · Library/Browse overflow + bottom-nav fixes · auto cache-bump deploys · configurator presets + Advanced.

## Top 10 Overall
Top 10 Overall
Priority | Initiative | Status | Detail / done this session
1 | Re-rank progress to a moving metric | Done | Layered 'Strong' metric — journey %, rank, chapters now advance on SRS box>=3 / 3-streak; Mastered * kept as deeper layer.
2 | Reviews Due as Home hero action | Done | Gold 'Review N due' hero on Home when reviews are due; new-session CTA demoted to outline (single focal point).
3 | Compose the session canvas / remove void | In Progress | Answered state + recall card composed, example fills the void. MC-drill / typed-question void still to do.
4 | Add production-output mode (writing/speaking) | Not Started
5 | Redesign answered state into one calm verdict | Done | One calm verdict block (SRS outcome + 5-dot mastery + quiet tutor link) replaces the 5-colour chip stack.
6 | Replace Browse with curated discovery | Not Started
7 | Aspirational empty states | Done | Done v2026.06.18.8 — first-run Progress shows an aspirational preview (Journey roadmap + Your-progress-live panel + Start-your-first-session CTA) instead of all-zero panels.
8 | CEFR validation and truthful B2 progress | Not Started
9 | Reposition around relocating professionals | Not Started
10 | AI Tutor productization (future premium launch feature) | Not Started

## Top 10 UX
Top 10 UX
Priority | Initiative | Status | Detail / done this session
1 | One dominant Home action | Done | Single dominant gold action on Home (Due when due, else Production); other actions demoted.
2 | Surface SRS Due queue as daily anchor | Done | SRS Due queue surfaced as the Home hero / daily anchor.
3 | Configurator → presets + Advanced | Done | SHIPPED v2026.06.18.7: topic setup leads with 3 one-tap presets (Quick/Standard/Deep); full controls behind 'Advanced options'. Special drills keep focused controls.
4 | Curated Browse experience | Not Started
5 | Compose session canvas | In Progress | Recall card eyebrow + answered verdict composed; remaining session screens pending.
6 | Redesign answered metadata stack | Done | Answered metadata stack redesigned into one verdict block.
7 | Remove redundant header eyebrows | Not Started
8 | Progressive disclosure in Progress/Stats | Not Started
9 | Unify naming and labels | Not Started
10 | Listening-first mode | Done | Listening-first dialogues: German hidden ('Tap to listen') until heard; Read-along toggle, persisted.

## Top 10 Learning
Top 10 Learning
Priority | Initiative | Status | Detail / done this session
1 | Layered mastery system | Done | Encountered -> Learning -> Strong -> Mastered; public progress advances on Strong.
2 | Speaking production mode | Not Started
3 | AI-graded writing | Not Started
4 | Hand-author irregular/modal grammar rules | Done | verbRule now flags present-irregular (modals, sein, wissen) + separable verbs; 'wollen -> ich will' no longer mislabelled 'keeps its stem'.
5 | Validate CEFR tags | Not Started
6 | Vocabulary-in-context practice | Done | Example sentence shown by default in production answered state, target word highlighted (data already on all 2,001 cards).
7 | Personalized weak-spot deck | Not Started
8 | Listening-first comprehension | Done | Listening-first comprehension in the 87 dialogues.
9 | Confusion-pair drilling | Not Started
10 | Exam-format practice | Not Started

## Top 10 Retention
Top 10 Retention
Priority | Initiative | Status | Detail / done this session
1 | Moving progress metric | Done | Moving 'Strong' progress metric (was welded to 5-in-a-row mastery).
2 | Reviews Due return trigger | Done | Reviews Due as the Home hero return-trigger.
3 | PWA reminders/notifications | Not Started
4 | Competence-based milestones | Not Started
5 | Adaptive daily plan | Not Started
6 | Weekly recap | Not Started
7 | Human progress language | In Progress | Headline copy now 'learned'/'solid' instead of 'mastered'; competence-based phrasing ('you can now...') still to come.
8 | Streak-freeze visibility | Not Started
9 | First-week aha sequence | Not Started
10 | Faster chapter progression | Done | Chapters fill on Strong, so a checkpoint / rank-up is reachable in days, not months.

## Top 10 Visual
Top 10 Visual
Priority | Initiative | Status | Detail / done this session
1 | Compose session canvas | In Progress | Recall card eyebrow + answered verdict + in-context example; MC/audio-style anchor for remaining screens pending.
2 | Screen-level focal point rule | In Progress | Home now has one gold focal action; not yet a systematic per-screen rule.
3 | Ration colour usage | In Progress | Answered state reduced to one accent colour; app-wide colour rationing pending.
4 | Redesign answered state | Done | Answered state redesigned into one calm verdict.
5 | Aspirational empty states | Done | SHIPPED v2026.06.18.8: brand-new Progress is no longer a wall of zeros — the B2 Journey roadmap leads, then a YOUR PROGRESS, LIVE panel previews Accuracy / Recall speed / Memory strength / Day streak with a Start your first session CTA. Gated on ds.attempts===0 so populated stats are unchanged.
6 | Improve Sentence Builder visual language | Not Started
7 | Improve Home hierarchy | Done | Home hierarchy: Due hero + demoted secondary CTAs; action now outranks the wordmark.
8 | Tighten card spacing | In Progress | Recall card balanced with an eyebrow; single-line vertical-centering still present elsewhere.
9 | Remove duplicate progress indicators | Not Started
10 | Use Audio mode as composition benchmark | Not Started

## Top 10 Wow
Top 10 Wow
Priority | Initiative | Status | Detail / done this session
1 | Speaking with pronunciation scoring | Not Started
2 | AI-graded writing feedback | Not Started
3 | Alive/composed session canvas | In Progress | Session canvas partially composed (answered state, recall card, in-context example); full 'alive' canvas pending.
4 | Relocation scenario packs | Not Started
5 | Goethe/telc exam mode | Not Started
6 | Adaptive coach-style daily plan | Not Started
7 | Competence unlocks | Not Started
8 | Enhanced mastery celebrations | Not Started
9 | Native-speed real-world audio | Not Started
10 | Shareable progress recap | Not Started

## Notes
Strategic Note
AI Tutor moved out of the immediate roadmap. It remains a strong future premium feature once AutoDeutsch launches publicly. Current priority should be progression, Home experience, session composition, guided learning, and production skills. Productizing the tutor makes more sense after the core product experience is polished and user demand is validated.
Additional changes shipped this session (not in the Top-10 lists):
Bug fix — horizontal scroll in Library / word Browse on narrow screens | Root cause was CSS grid min-width:auto blow-out (cards couldn't shrink, 'Known' button overhung). Fixed with grid minmax(0,1fr) + minWidth:0 + ellipsised text, plus a global html/body overflow-x:hidden guard. Verified clean 280-390px. (user-reported)
Deploy reliability — service-worker cache auto-invalidation | build now derives CACHE_NAME from a content hash of app.js + data.js + index.html, so every deploy reaches installed PWAs (previously a manual, easily-missed step). APP_VERSION bumped each release for in-app verification (Settings -> Current build).
Tooling — responsive overflow audit in the screenshot harness | Added SHOOT_WIDTH + SHOOT_OVERFLOW to scripts/shoot.mjs to catch this class of layout bug automatically at narrow widths.
Deployment | All of the above deployed to main (GitHub Pages). Current build: 2026.06.18.3.
Legend | Status: Done = implemented & deployed this session. In Progress = partially shipped. Not Started = unchanged.

## New Ideas
New Ideas (user-added backlog)
Idea | Category | Feasibility | Status | Detail / notes
Settings cog rotates on tap to match the nav-tab icon animation; static icons (e.g. chip) pulse | Visual / Delight | Feasible now — quick win | Done | Icons are single-path SVGs. Cog: add a rotate keyframe fired on click (the nav tabs already use a scale 'ad-tab-pop'). Pulse = scale/opacity loop. Low risk, ~1 small change. [SHIPPED v2026.06.18.4: cog spins on tap; static icons (chip etc.) animate; delegated WAAPI listener covers every icon button.]
Bespoke, in-character icon animations on interaction — every icon reacts like the active nav-tab icon (e.g. lightning bolt shoots down, house constructs, book opens & closes, hand closes, chip pulses) | Wow / Delight | Partial — feasible subset now; full morphs are high-effort | In Progress | Feasible NOW on the existing single-path STROKE icons: stroke-dashoffset 'draw-on' (house 'constructs'), translate/fade (bolt 'shoots down'), rotate (cog), pulse (chip), pop. TRUE shape-morphs (a hand closing, a book opening/closing) can't be done on one static path — each needs redesigning as a multi-element / morphable SVG, or a Lottie-style asset (bigger design+eng project). Recommended path: ship cog + pulse + draw-on/pop first (covers most of the delight at low risk), tackle bespoke morphs icon-by-icon later. [SHIPPED v2026.06.18.4 — feasible tier: spin/drop/build/swing/pulse/beat/pop mapped per icon, played on tap app-wide. REMAINING: true shape-morphs (hand closing, book opening) need per-icon SVG redesign.]